## March 2025
These contracts are planned for advertisement by the Washington State Department of Transportation for Mar 1, 2025 through Feb 28, 2026. Only one state route is displayed per project. Some types of projects, e.g., chip seals, bridge painters, seismic retrofits, electrical updates, and guardrail updates, may involve regionwide work. For projects with fish barrier corrections, the fish passage Site Id(s) are listed in the comments. Please note the advertisement dates are tentative and some information may change after this report is issued. Projects are dependent on funding availability. For current information, please visit the Contract Ad and Award website at https://wsdot.wa.gov/business-wsdot/contracts/about-public-works-contracts/alerts-bulletins/contracts-planned-advertisement
*ESHB 2134, Section 502 requires that:
TRANSIT, BICYCLE, AND PEDESTRIAN ELEMENTS REPORTING By November 15th of each year, the department of transportation must report on amounts expended to benefit transit, bicycle, or pedestrian elements within all connecting Washington projects in programs I, P, and Z identified in LEAP Transportation Document 2024-2 ALL PROJECTS as developed March 6, 2024, in a manner consistent with past practices as specified in section 602, chapter 186, Laws of 2022.
Design Build
Request for Qualifications (RFQ) / Ad Date | Type | Cost Range | Region | SR | Title and Work Description | County | WI Number | State | *502 | Comments
2025-08-15 | Unique | 100-150M | 405 | 518 | SR 518/Tukwila International Boulevard Bus Rapid Transit Station Project Construct Transit Station Building, Pedestrian Bridge, and Roadway Restoration | King | A51801C |  |  | Site ID: 998886, Funded by Sound Transit
Design Bid Build
Request for Qualifications (RFQ) / Ad Date | Type | Cost Range | Region | SR | Title and Work Description | County | WI Number | State | *502 | Comments
2025-03-17 | Resurface | 3 - 4M | South Central | 012 | US 12 Howell Grade Rd to Garfield-Asotin County line - Paving Grind and repave HMA | Garfield | E01219W | X |  | Anticipated mix design information: Class 3/8" PG 64H-28, 1.6 M ESALs
2025-03-24 | Resurface | 4 - 5M | Eastern | 021, 260 | 2025 Eastern Region Chip Seal Chip Seal with Basic Safety Restoration on SR 21 and SR 260 | Adams, Franklin | F02100U
2025-03-24 | Unique | 5-10M | Southwest | 014 | SR 14/Bingen Overpass Construct grade separated rail crossing | Klickitat | D01419B | X | X
2025-03-24 | Resurface | 5-10M | North Central | 002 | US 2 Coles Corner Vicinity - Paving HMA Overlay | Chelan | B00206X
2025-03-31 | Resurface | 5 - 10M | Northwest | 525 | SR 525 I-405 I C to SR 99 Vicinity - Paving & ADA Compliance HMA Paving and ADA Compliance | Snohomish | A52500D
2025-03-31 | Resurface | 15/20M | North Central | 090 | I-90 E of Vantage to Moses Lake - Paving Mill and fill | Grant | B09000P |  |  | Anticipated mix design information: Class 1/2" PG 64V-28, >10 M ESALs
2025-03-31 | Resurface | 5 - 10M | Eastern | 395 | US 395 Lind Coulee Bridge to I-90 - SB Lanes Only - Paving HMA paving with basic safety restoration | Adams | F39508B
2025-04-07 | Safety | 0 - 1M | North Central | 282 | SR 282 Nat Washington Way - Roundabout Construct roundabout | Grant | B28201E | X
2025-04-07 | Unique | 20-25M | Southwest | 105 | SR 105/Graveyard Spit - Dynamic Revetment and Dune Restoration Construct an innovative nature-base dune and cobble berm | Pacific | D10524E
2025-04-07 | Unique | 1 - 2M | North Central | 002 | US 2 West of Leavenworth - Slope Stabilization Slope Stabilization | Chelan | B00209M
2025-04-14 | Unique | 0 - 1M | Northwest | 005 | I-5 NB Spokane St - Ramp Meter Installation Ramp Meter Installation | King | A00526Q
2025-04-14 | Resurface | 4 - 5M | Eastern | 395 | US 395 Hafer Rd to Chewelah - Paving Hot Mix Asphalt paving with basic safety restoration & Complete Streets | Stevens | F39520C |  |  | Anticipated mix design information: Class 3/8" PG 64H-28, 2.3 M ESALs
2025-04-14 | Resurface | 5 - 10M | Northwest | 090 | I-90 EB West Lake Sammamish Parkway to E Sunset Way - Paving HMA Paving | King | A09055F |  |  | Anticipated mix design information: Class 1/2" PG 58V-22, 15.7 M ESALs
2025-04-16 | Resurface | 1 - 2M | Ferries | 305 FT WINSLO | SR 305 Bainbridge Island Trm - NE Parking Lot Pavement Rehabilitation - Resurfacing/rehabilitation of upland parking area | Kitsap | M03480A | X
2025-04-21 | Safety | Under 1M | Southwest | 142 | SR 142/0.7 Miles E of Appleton Rd to School Dr - Trail Improvements Upgrade ADA facilities within the limits of the paver 414214P | Klickitat | D14214C | X
2025-04-21 | Resurface | 5-10M | Southwest | 005 | I-5/0.1 Miles N of Koontz Rd to SR 507 - Paver Hot Mix Asphalt (HMA) Grind and Inlay | Lewis | D00526Y | X
2025-04-21 | Unique | 0 - 1M | Southwest | 432 | SR 432 Washington Way Signal Replacement Upgrade Signal System | Cowlitz | D43216S
2025-04-21 | Resurface | 2 - 3M | Eastern | 395 | US 395 Chewelah to Immel Rd - Paving Asphalt Paving with Basic Safety Restoration | Stevens | F39520J |  |  | Anticipated mix design information: Class 3/8" PG 64H-28, 2.3 M ESALs
2025-04-21 | Resurface | 5 - 10M | Olympic | 512 | SR 512 W of Canyon Rd to 31st Ave SW - Paving | Pierce | C51216H
2025-04-21 | Resurface | 2-3M | Olympic | 101 | US 101 Skookum Creek Br to N of Jct SR 8 - Paving HMA Grind & Inlay | Mason, Thurston | C10167P |  |  | Anticipated mix design information: Class 1/2" PG 58H-22, 3-10 M ESALs
2025-04-21 | Resurface | 5 - 10M | Northwest | 090 | I-90 WB SR 900 Vic to E Sunset Way - Paving & ADA, and Expansion Joints HMA Paving & ADA and Expansion Joints - Br 90/63N, 90/65N, 90/66N | King | A09056B |  |  | Anticipated mix design information: Class 1/2" PG 58H-22, 19 M ESALs
2025-04-22 | Bridge | 20 - 25M | Ferries | 525 FT MUKILT | SR 525 Mukilteo Trm - Left Wingwall Rehabilitation and Repair Left Wingwall Rehabilitation and Repair | Snohomish | M04422A | X
2025-04-28 | Unique | 1-2M | Southwest | 508 | SR 508/0.3 Miles E of Bergen Road - Engineered Log Jam Embankment protection to prevent erosion of the highway | Lewis | D50825J
2025-04-28 | Resurface | 1 - 2M | Northwest | 099 | SR 99 Tunnel - Pavement Texturing Pavement Texturing | King | A09940A | X
2025-04-28 | Resurface | 3 - 4M | Eastern | 195 | US 195 SR 27 to Babbit Rd - Paving HMA paving with basic safety restoration | Whitman | F19502E
2025-04-28 | Resurface | 2 - 3M | Eastern | 002 | US 2 South Shore Rd to Newport - Paving Asphalt Paving with basic safety restoration | Pend Oreille | F00232W
2025-04-28 | Resurface | 1 - 2M | Olympic | 005 | I-5 Maytown Rd to Plum St - Paving HMA Inlay | Thurston | C00503C
2025-04-28 | Resurface | 15 - 20M | Olympic | 003, 016 | SR 3 and SR 16/Kitsap Vicinity - Paving HMA Inlay | Kitsap | C00399B |  |  | Anticipated mix design information: Class 1/2" PG 58H-22, 3-10 M ESALs
2025-04-28 | Emergency | 10-15M | Olympic | 112 | SR 112 E of Sail River to E of E Twin River – Paving Preservation and Emergency Embankment slope stabilization, Slope ID #3747 | Clallam | C11272E
2025-05-05 | Resurface | 2-3M | South Central | 821 | SR 821 I-82 to Selah Creek - Paving Grind and repave HMA | Yakima | E82101Y |  |  | *Subject to change based on outcomes from the 2025 legislative session. Anticipated mix design information: Class 3/8" PG 64H-28, 1.25 M ESALs.
2025-05-05 | Bridge | 2 - 3M | South Central | 124 | SR 124 US 12 Interchange EB - Bridge Repair Emergency Bridge Repair | Walla Walla | E12403S |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-12 | Resurface | 3 - 4M | Northwest | 090 | I-90 EB Mercer Slough to 150th Ave SE - Paving & Bridge Deck Resurface HMA Paving and Bridge Deck Resurface Br 90/50S | King | A09052N |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-12 | Resurface | 5 - 10M | Eastern | 090 | I-90 BNRR Bridge to Geiger Rd - Paving HMA paving with basic safety restoration | Spokane | F09027V |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-12 | Resurface | 5 - 10M | Northwest | 005 | I-5 SB 100Th St SE Vic to Broadway Ave - Paving HMA Paving | Snohomish | A00536E |  |  | *Subject to change based on outcomes from the 2025 legislative session. Anticipated mix design information: Class 1/2" PG 58V-22, 29.2 M ESALs.
2025-05-12 | Unique | 5-10M | South Central | 082 | I-82/2 miles E of Donald Rd - Culvert Replacement Replace culvert | Yakima | E08211Z |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-12 | Safety | 2 - 3M | Eastern | 090 | I-90 Guardrail Basic Safety - Rehabilitation Remove, replace and rehabilitate existing guardrail | Adams,Lincoln,Spokane | F09019G |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-19 | Unique | 20 - 25M | South Central | 224 | SR 224 Red Mountain Vicinity Improvements Improve intersections, add lanes and bike & pedestrian facilities | Benton | E22407R | X | X
2025-05-19 | Bridge | 5 - 10M | Northwest | 090 | I-90 EB Mercer Slough Bridge - Rehabilitation Bridge Rehabilitation Br 90/43S | King | A09029A |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-05-19 | Safety | 2-3M | Olympic | Multiple Routes | SR 702, SR 510, & SR 507 CRAB Bundle #1A Construct compact roundabouts | Pierc, Thurston | C50742R |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-06-02 | Resurface | 5-10M | South Central | 024, 240 | SR 240/SR 24 Intersction Vicinity - Paving Grind and repave HMA | Benton | E24002T |  |  | *Subject to change based on outcomes from the 2025 legislative session. Anticipated mix design information: Class 1/2" PG 64H-28, 4.25 M ESALs.
2025-06-02 | Bridge | 0 - 1M | Northwest | 099 | SR 99 1st Ave S Bridge-Tower Mitigation & Watertight Door Replacement Replace Watertight Door - Bridges 99/530E & 99/530W | King | A09926V |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-06-02 | Unique | 0 - 1M | Northwest | Regionwide | I-90, SR 202, SR 203, & SR 900 - Adaptive Management Adaptive Management of 4 sites | King | A00022H | X |  | Site Id(s): 996963, 102 L062, 995181, & 991842 *Subject to chage based onoutcomes from the 2025 legislative session.
2025-06-16 | Bridge | 0 - 1M | Southwest | 014 | SR 14 E of Slide Bridge - Repair Crib Wall Repair or replace deteriorating timber crib wall just east of Br. 14/104 | Skamania | D01414G |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-06-16 | Unique | 3-4M | Olympic | Regionwide | 2023 Regionwide Adaptive Management - Fish Passage Barrier Repairs (18.0021 5.40,22.0507 0.10,990178,990400,996735) | Clallam,Grays Harbor,Jefferson,Mason | C00023F | X |  | Site Id(s): 18.0021 5.40; 22.0507 0.10; 990178; 990400; 996735 *Subject to change based on outcomes from the 2025 legislative session.
2025-06-23 | Unique | 0 - 1M | Olympic | 106 | SR 106 McReavy Rd Vicinity - Culvert Repair Repair existing culvert WSDOT0000786471 | Mason | C10612B | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-06-23 | Unique | 2 - 3M | Olympic | 112 | SR 112 Clallam Bay 2023 - Emergency Project Repair unstable slope #2947 | Clallam | C11215E |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-06-30 | Unique | 5 - 10M | Ferries | 519 FT SEATTL | SR 519 Seattle Trm - Pile Corrosion mitigation Pile Corrosion mitigation | King | M04879A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-07-07 | Bridge | 5 - 10M | Northwest | 529 | SR 529 SB Steamboat Slough Bridge - Bridge Painting Bridge Painting Bridge 529/20W | Snohomish | A52906K |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-07-07 | Unique | 4 - 5M | Ferries | 305 FT EAGHBR | SR 305 Eagle Hbr Maint Facility - Welding Shop Building Replacement Replacement of existing welding shop building on Slip E trestle | Kitsap | M03731A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-07-21 | Safety | 4 - 5M | Southwest | 500 | SR 500 NE Robinson Rd and NE 3rd St - Intersection Safety Improvements Improve safety at two intersections | Clark | D50018S |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-08-04 | Bridge | 4 - 5M | Southwest | 504 | SR 504 Spirit Lake Outlet Br - Emergency Replacement Replacing Bridge #504/107 - Spirit Lake Outlet Br | Skamania | D50424F |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-08-04 | Safety | Under 1M | Southwest | 004 | SR 4/Crawford Bridge Pedestrian Illumination | Cowlitz | N/A |  |  | Z2 Funded Project
2025-08-11 | Bridge | 30 - 35M | Ferries | 304 FT BREMER | SR 304 Bremerton Trm Slips 1 & 2 - Vehicle Transfer Span Replacement Replace existing movable bridges 304/18FT and 304/15FT | Kitsap | M03534A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-02 | Unique | 1 - 2M | Capital Facilities |  | Bingen SMF - Wash Pad Water Remediation - NPDES - SWR Install new wash pad and heated wash bay - BIN D311701 | Klickitat | S88843T | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-08 | Bridge | 5 - 10M | Northwest | 099 | SR 99 Spokane Street Bridge - Expansion Joint Modification Expansion Joint Modification Bridge 99/538 | King | A00502C |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-15 | Safety | 3 - 4M | Northwest | 020 | SR 20 Campbell Lake Road - Intersection Improvements (Local-WSDOT Lead) Construct Three-Legged Roundabout (GCB 3267) | Skagit | A02028E |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-22 | Major Construction | 5-10M | Olympic | 162 | SR 162 SR 410 Interchange - Construct Roundabouts Design for the SR 162/SR410 roundabouts | Pierce | C16202C | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-22 | Bridge | 4 - 5M | Northwest | 536 | SR 536 Skagit River Bridge - Painting Paint existing structure Br 536/15 | Skagit | A53607D |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-09-26 | Unique | 1 - 2M | Ferries | 163 FT PTDEFI | SR 163 Point Defiance Trm - Toll Booth 1 Toll Booth 1 | Pierce | M04618A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-06 | Major Construction | 100 - 200M | Eastern | 395 | US 395 NSC Sprague Ave to Spokane River - Stage 2 Construct new lanes | Spokane | F00015P | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-06 | Safety | 15 - 20M | Northwest | 090 | I-90 EB Weigh Station Construct weigh station on EB I-90 | Kittitas | A09070J |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-20 | Bridge | 5 - 10M | Eastern | 195 | US 195 Colfax North Fork Palouse River - Replace Bridges Replace two bridges with one and realign intersection | Whitman | F19503P |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-20 | Major Construction | 20 - 25M | Northwest | 005 | I-5 Slater Road Interchange - Roundabouts & Improvements Construct Roundabouts and Improvements | Whatcom | A00598R | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-20 | Major Construction | 0 - 1M | Northwest | 203 | SR 203 Slough Bridge Vic to Kelly Rd NE Vic-Stormwater Retrofit Stormwater Retrofit | King | A20314B |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-20 | Safety | 0 - 1M | Northwest | 546 | SR 546 Benson Road - Intersection Improvements Compact Roundabout | Whatcom | A54600I |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-10-20 | Unique | 10 - 15M | Northwest | 544 | SR 544 Nooksack River Overflow Culvert - ER Permanent Repair Damaged Culvert Replacement | Whatcom | A54407A |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-03 | Bridge | 15 - 20M | Northwest | 090 | I-90 Homer M Hadley & Lacey V Murrow Bridges-Access Hatch & Electrical Special Bridge Repair and Electrical Rehabilitation - 90/25N & 90/25S | King | A09014E |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-03 | Major Construction | 2 - 3M | Northwest | 090 | SE 104th St Stream Restoration Stream Restoration | King | A09070L |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-03 | Resurface | 5 - 10M | Southwest | 005 | I-5 SB I-205 to NE 179th St Concrete Pavement Rehabilitation Crack and Seat Concrete and Overlay with asphalt and rebuild shoulder | Clark | D00525E |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-03 | Safety | 2 - 3M | South Central | 022 | SR 22 SR 223 Chambers Rd Intersection - Intersection Safety Construct intersection safety improvements | Yakima | E02202Z |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-03 | Unique | 10 - 15M | Northwest | 000 | NWR I-90 & I-5 Tunnel Fire Suppression Systems - Retrofit Retrofit Fire Suppression System | King | A00021N |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-10 | Bridge | 0 - 1M | Eastern | 194 | SR 194 Busch Bridge at Port of Almota - Bridge Rehab Rehab Bridge 194/1 with new concrete deck surface and modify girders | Whitman | F19400L |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-17 | Unique | 2-3M | South Central | 125 | SR 125/Plaza Way - Railroad Crossing Improvements Construct railroad crossing and sidewalk improvements - Xing 808942N | Walla Walla | E12502R |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-17 | Major Construction | 45-50M | Olympic | 510 | SR 510 Yelm Loop - New Alignment Phase 2 New alignment | Thurston | C51029A | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-17 | Safety | 3 - 4M | Olympic | 162 | SR 162 Orville Rd E Intersection - Roundabout Construct a roundabout | Pierce | C16211R |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-17 | Bridge | 5 - 10M | Ferries | 020 | Systemwide Type 3 VTS upgrades (elec mech rehab) VTS Mech/elec system Rehab at Orcas/Lopez/Coup/Ed/Ana Terminals | San Juan,Skagit,Snohomish | M04530B | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-19 | Unique | 2 - 3M | Ferries | 104 FT EDMOND | SR 104 Edmonds Trm - Tollbooth Replacement Replace/Renovate three existing upland toll booths | Snohomish | M03832A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-19 | Unique | 3 - 4M | Ferries | 305 FT WINSLO | SR 305 Bainbridge Island Trm - Electrical Connection for Hybrid Electrical to Bainbridge Island Terminal for Hybrid Vessel | Kitsap | M03444A | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-19 | Unique | 4 - 5M | Ferries | 525 FT CLINTN | SR 525 Clinton Trm - Electrical Connection for Hybrid Electrical to Clinton Terminal for Hybrid Vessel | Island | M03623A |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-19 | Unique | 5 - 10M | Ferries | 525 FT CLINTN | SR 525 Clinton Trm - Terminal Electrification Terminal Electrification | Island | M03623B |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-11-24 | Bridge | 1 - 2M | Southwest | 005 | I-5 Koontz Rd Bridge - Emergency Bridge Repair Repair damage to bridge 005/212 from Third Party | Lewis | D00524K |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-08 | Major Construction | 55 - 60M | Eastern | 395 | US 395 NSC I-90 Improvements - Hamilton to Thor Construct I-90 ramps and city streets to accommodate NSC/I-90 I/C | Spokane | F00016B | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-15 | Resurface | 20-25M | Olympic | 101 | US 101 N of Ocean Beach Rd to Jefferson Co Line - Paving HMA Inlay | Grays Harbor | C10192H |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-15 | Safety | 2 - 3M | Olympic | 702 | SR 702 8th & 40th St - CRAB Bundle #1B | Pierce | C70205A |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-15 | Safety | 5 - 10M | Northwest | 002 | US 2 Corridor Safety Improvements Corridor Safety Improvements | Snohomish | A00217A | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-15 | Resurface | 5 - 10M | Northwest | 020 | SR 20 Burlington to Sedro-Woolley - Corridor Improvements Corridor Improvements | Skagit | A02061A |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-15 | Unique | 1 - 2M | South Central | 395 | US 395 Kartchner St I C - NB Ramp Terminal Improvements Construct compact roundabout | Franklin | E39508Q | X |  | *Subject to change based on outcomes from the 2025 legislative session.
2025-12-22 | Safety | 3 - 4M | Olympic | 160 | SR 160 Long Lake Rd SE - Roundabout Construct a roundabout | Kitsap | C16011B |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-01-12 | Safety | 0 - 1M | South Central | 012 | US 12 Ackley Rd Clover Lane - Intersection Safety Improvements Construct intersection improvements | Yakima | E01216Z |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-01-12 | Safety | 1 - 2M | South Central | 012 | US 12 Eschbach Rd - Intersection Safety Improvements Construct intersection improvements | Yakima | E01216X |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-01-12 | Safety | 1 - 2M | Southwest | 012 | US 12 SR 7 - Intersection Improvements Construct safety improvements at intersection of US 12 and SR 7 | Lewis | D01223I |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-01-26 | Major Construction | 35 - 40M | Olympic | 003 | SR 3 Freight Corridor - New Alignment Construct new alignment | Kitsap,Mason | C00344E | X | X | *Subject to change based on outcomes from the 2025 legislative session.
2026-02-17 | Resurface | 0 - 0M | Southwest | 012 | US 12 I-5 to 0 5 Mile East of Harms Rd - Paving | Lewis | D01218P |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-02-23 | Safety | 1 - 2M | South Central | 241 | SR 241 Allen Rd Intersection - Intersection Safety Construct compact roundabout | Yakima | E24103H |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-02-23 | Bridge | 1 - 2M | Olympic | 012 | US 12 Heron St Bridge - Grid Deck Replacement Replace bridge grid deck | Grays Harbor | C01228T |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-02-23 | Safety | 1 - 2M | South Central | 241 | SR 241 E Edison Rd Intersection - Intersection Safety Construct compact roundabout | Yakima | E24103I |  |  | *Subject to change based on outcomes from the 2025 legislative session.
2026-02-23 | Resurface | 15 - 20M | Northwest | 525 | SR 525 SR 525 Spur Vic to Mukilteo Ferry Terminal - Paving & ADA HMA Paving and ADA compliance | Snohomish | A52505B |  |  | *Subject to change based on outcomes from the 2025 legislative session.